# Hopscotch vLLM Migration Plan

Ollama → vLLM  |  1-Week Implementation Plan

# Overview

This document outlines a 7-day plan to migrate the Hopscotch IRML platform from Ollama (local, serialized inference) to vLLM (high-throughput, batched inference) on a GPU cluster. The goal is to support ~50 concurrent users during pilot testing with AP Research high-school students without latency degradation.

# Current Architecture

| Component | Current Setup | Notes |
| --- | --- | --- |
| Primary LLM | Qwen 2.5 14B via Ollama | Serialized requests, single-user queue |
| Embedding Model | all-MiniLM-L6-v2 (384-dim) | Used for RAG, runs on CPU |
| Backend | FastAPI + Uvicorn on port 9580 | Hosted on Lambda machine |
| Frontend | React 19 + Vite on port 9581 | Served via static build |
| Database | MongoDB (local, port 27017) | Stores users, sessions, chat history |

# The Problem

Ollama serializes inference requests — each student's chat query waits in a queue. With a single GPU, this means:

1 user: ~8–12 second response time (acceptable)

10 concurrent users: ~60–90 seconds each (poor experience)

50 concurrent users: timeouts and crashes (unusable)

vLLM solves this with continuous batching — it processes multiple requests simultaneously on the GPU, dramatically reducing per-user latency under load.

# Day-by-Day Implementation Plan

## Day 1 (Monday) — Backend Abstraction Layer

Goal: Decouple LLM calls from Ollama so they work with any OpenAI-compatible API (which vLLM exposes natively).

Changes in app_chat.py:

Replace hardcoded Ollama config (OLLAMA_URL, OLLAMA_BASE, LLM_MODEL) with environment variables:
    • LLM_ENDPOINT → vLLM's /v1/chat/completions URL
    • LLM_API_KEY → optional auth token
    • LLM_MODEL → "Qwen/Qwen2.5-14B-Instruct"

Rename build_ollama_payload() → build_llm_payload() to output OpenAI-format messages.

Update call_llm() to parse choices[0].message.content instead of Ollama's message.content format.

Update _warm_ollama_model() to hit the vLLM /health endpoint instead of Ollama's /api/chat.

No frontend changes required — the API contract between frontend and backend stays identical.

## Day 2 (Tuesday) — Streaming Rewrite

Goal: Update the /chat/send_stream endpoint to work with vLLM's Server-Sent Events (SSE) format.

Current behavior:

Ollama streams: {"message": {"content": "token"}} per line

vLLM behavior:

vLLM streams: data: {"choices": [{"delta": {"content": "token"}}]} with a data: [DONE] sentinel

Changes required:

Update the iter_lines() parser in /chat/send_stream to handle SSE data: prefix.

Handle the [DONE] sentinel to close the stream cleanly.

Ensure the finally block still assembles the full response and persists it to MongoDB.

Test with a local vLLM instance to confirm streaming works end-to-end.

## Day 3 (Wednesday) — vLLM Deployment on GPU Cluster

Goal: Get vLLM serving Qwen 2.5 14B on the GPU cluster.

Steps:

1. SSH into GPU cluster and install vLLM: pip install vllm

2. Download model weights: huggingface-cli download Qwen/Qwen2.5-14B-Instruct

3. Launch vLLM server:
    vllm serve Qwen/Qwen2.5-14B-Instruct \
      --host 0.0.0.0 --port 8000 \
      --max-model-len 8192 \
      --tensor-parallel-size 1 \
      --gpu-memory-utilization 0.9

4. Verify with a curl test against /v1/chat/completions.

5. If multiple GPUs are available, set --tensor-parallel-size 2 to split the model across GPUs for faster inference.

Hardware Requirements: Qwen 2.5 14B requires ~28 GB VRAM in FP16, or ~14 GB in INT8/AWQ quantization. A single A100 (40 GB) or two A10G (24 GB each with tensor parallelism) are recommended.

## Day 4 (Thursday) — Connect Lambda ↔ GPU Cluster

Goal: Point the Hopscotch backend on the Lambda machine to the remote vLLM server on the GPU cluster.

Steps:

1. Set environment variables in ecosystem.config.cjs:
    LLM_ENDPOINT: "http://<cluster-ip>:8000/v1/chat/completions"
    LLM_MODEL: "Qwen/Qwen2.5-14B-Instruct"

2. Restart backend via PM2: pm2 delete hopscotch-backend && pm2 start ecosystem.config.cjs --only hopscotch-backend

3. Test both endpoints manually:
    • /chat/send (non-streaming) — should return full response
    • /chat/send_stream (streaming) — should stream tokens in real time

4. Update watchdog.sh to also health-check the vLLM endpoint on the cluster.

## Day 5 (Friday) — Load Testing (50 Concurrent Users)

Goal: Verify the system handles pilot-scale load with acceptable response times.

Test plan:

Write a load test script (Python + asyncio + httpx) simulating 50 concurrent /chat/send requests with realistic prompts.

Measure: time-to-first-token, total response time, error rate, GPU utilization.

Expected performance comparison:

| Metric | Ollama (Current) | vLLM (Target) |
| --- | --- | --- |
| 1 user latency | ~8–12 seconds | ~5–8 seconds |
| 10 concurrent users | ~60–90 seconds each | ~8–15 seconds each |
| 50 concurrent users | Timeout / crash | ~15–30 seconds each |

vLLM tuning parameters if needed:

--max-num-seqs 64 — maximum concurrent sequences

--max-model-len — reduce if memory-constrained

--enable-prefix-caching — huge win because the ~700-line system prompt is identical for all users; vLLM caches the KV values and reuses them across requests

## Day 6 (Saturday) — Fallback & Reliability

Goal: Make the system production-safe with automatic fallback.

Implementation:

Add Ollama fallback — if vLLM is unreachable, automatically fall back to local Ollama on the Lambda machine. This ensures zero downtime even if the GPU cluster has issues.

Update watchdog.sh to monitor vLLM health via: curl -s http://<cluster-ip>:8000/health. Log warnings if vLLM is down, but don't crash the backend — the fallback handles it.

Run pm2 save and test a full reboot cycle on the Lambda machine to verify everything comes back automatically.

Verify the cron watchdog (every 2 minutes) correctly detects and restarts failed services.

## Day 7 (Sunday) — End-to-End Verification & Cleanup

Goal: Full system test through both production domains.

Test checklist:

Test from both hopscotch4all.com and hopscotchai.us

Login → Create session → Chat on Steps 1–9 → Verify RAG kicks in at Step 4+

Verify streaming works in the UI (tokens appear incrementally)

Teacher feedback flow (post feedback, student reads it)

PDF export of research design

Admin dashboard loads correctly with stats

Cleanup:

Remove old hardcoded OLLAMA_URL / OLLAMA_BASE values from app_chat.py.

Create a .env.example file documenting the new environment variables.

Email Dylan and Dr. Zhang confirming deployment is live and ready for pilot testing.

# Model & Infrastructure Details

For reference — details to share with the deployment team:

| Parameter | Value |
| --- | --- |
| Primary LLM | Qwen 2.5 14B Instruct (Apache 2.0 license) |
| HuggingFace ID | Qwen/Qwen2.5-14B-Instruct |
| Model Size | ~9 GB on disk, ~28 GB VRAM (FP16) |
| Embedding Model | sentence-transformers/all-MiniLM-L6-v2 (384-dim, CPU) |
| Vector Store | FAISS (IndexFlatIP, ~18 PDF documents indexed) |
| Database | MongoDB 7.x (local, port 27017) |
| Inference Server | vLLM (target) / Ollama (fallback) |

# Key Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Network latency between Lambda and GPU cluster | Streaming feels sluggish | Move entire backend to GPU cluster, or ensure same campus network |
| GPU cluster access delayed | Blocks Day 3–5 | Use Modal.com ($30/mo free academic tier) as interim GPU host |
| vLLM OOM with 50 concurrent users | Requests fail | Reduce --max-model-len, use AWQ quantization, or add tensor parallelism |
| MongoDB single point of failure | Data loss | Migrate to MongoDB Atlas (free tier) for managed backups and replication |

# Alternative Deployment Options (from Dylan Goldblatt)

Dylan recommended three options. This plan follows Option 1 (vLLM), but the others remain viable alternatives:

| Option | Cost | Effort | Best For |
| --- | --- | --- | --- |
| 1. vLLM on GPU cluster | Free (own GPU) | Medium | Full control, best throughput |
| 2. HuggingFace Inference Pro | $9/month | Low | Fastest to deploy, no infra management |
| 3. Modal.com serverless | $30/mo free (academic) | High | Scale to zero, pay per second |

Prepared by Mourya Tatiparthi  |  April 2026